## Organization
Ranking |  | Initiative | Ntn'l Main Street | Notes | Person(s) Responsible | Start Date | Target Date | Measure of Success
PRIORITIES: | 1 | SPARC | physical improvements | Spaces Parks, Art Recreation, Community | committee | January | on-going | continued improvements to public spaces
|  | Park at 336 | Completion and Recognition | Gate lock, story/donnor panel, reg. signs, landscaping, assess installation at west wall | committee | March | 2021-06-22 | Lock, signs/landscaping installed (tree), west wall assessed and designed.
|  | Riverwalk Assessment | Physical Improvements | Planning and advocacy for 5 year improvement plan | committee | June | Dec | Enhancements and improvement for increased identity and use
|  | Future Targeted Areas for Development | Identify, Expanded Use, Improvements | Library Park, Church Mini-Park, Putnam Plaza | Committee, Ownership | July | Nov | Enhancements and improvement for increased identity and use
| 2 | DOWNTOWN ENVIRONMENT | physical improvements
|  | Pedestrian Spaces | Identify, Expanded Use, Improvements | assess areas for redesign: Franklin Lane, alleyways, Putnam Sq. streetscape, furnishings | committee, Town, BRG | January | Aug | rethink how new downtown environment will utilize public spaces
|  | Putnam Square Kiosk, Mini Kiosks and Wayfinding |  | indentify additional informational signage | committee, Community Development | January | Dec | improved imformational and instructional signage
|  | Better Places Grants | physical enhancments | winter lights, banners, BIB, flags, etc... | Committee, BBC | March | May | plan in place to apply for grant
|  | Downtown Transportation Grants |  | Provide input on projects to be selected and grant application | Comm. & Town's Community Dev. Office | Sept | Dec | proposal made to town
ONGOING: | 1 | BIB and Street Furnishings | planning and design | continue to work with town on layout and improvements | committee, BIB, town staff | Feb | on-going
| 3 | Awards Program/Communiuty Accomplishments | partnerships | Provide recommendations to Organization Committee, promote downtown developmemt | Committee | January | June | improvements to be recognizedand development recognized