## Feb 2024
Actual Contact | Service Request # | Summary | Status *(See Next Tab for Explanation) | Actual Finish
2024-02-01 08:27 | 24011584 | NEQ Pothole Patching-13225 E Placita Las Avenas | RESOLVED | 2024-02-29 13:07
2024-02-01 12:10 | 24011602 | NEQ Pothole Patching ---3998 N Sutton Ln | RESOLVED | 2024-02-26 06:23
2024-02-01 13:30 | 24011613 | SWQ Pothole Patching-- 4500 S Paseo Don Carlos & S Placita Don Felix | RESOLVED | 2024-02-02 15:08
2024-02-01 13:32 | 24011614 | SWQ Pothole Patching-- 4800 W Paseo Don Carlos & S Seymour Rd | RESOLVED | 2024-02-01 15:34
2024-02-01 13:33 | 24011615 | SWQ Pothole Patching--S Seymour Rd | RESOLVED | 2024-02-01 15:34
2024-02-01 13:37 | 24011617 | SWQ Pothole Patching--4213 S Camino de Oeste MC | REFERRED | 2024-02-05 15:36
2024-02-01 14:42 | 24011640 | NEQ Pothole Patching-E Cloud Rd & N Camino de Piedras, | RESOLVED | 2024-02-26 06:21
2024-02-01 16:00 | 24011648 | NWQ Pothole Patching -7409 North Boston Place | RESOLVED | 2024-02-13 05:56
2024-02-01 16:02 | 24011649 | SWQ Pothole Patching - S Cherokee Ln | RESOLVED | 2024-02-28 05:50
2024-02-02 13:17 | 24011691 | NWQ Pothole Patching -5601-6399 N Panorama Dr | RESOLVED | 2024-02-14 06:19
2024-02-02 15:14 | 24011701 | SWQ Pothole Patching - W Scotland St | RESOLVED | 2024-02-28 05:50
2024-02-03 15:59 | 24011714 | SEQ Pothole Patching--3169 S Avenida los Reyes | RESOLVED | 2024-02-20 08:03
2024-02-03 18:10 | 24011715 | NEQ Pothole Patching–2765 N Tomahawk Trail | RESOLVED | 2024-02-26 06:24
2024-02-03 20:35 | 24011717 | NWQ Pothole Patching-N La Cholla Blvd & W Overton Rd | RESOLVED | 2024-02-14 05:46
2024-02-03 21:42 | 24011719 | NWQ Pothole Patching-N Tovar av | RESOLVED | 2024-02-08 07:04
2024-02-04 11:46 | 24011722 | NWQ Pothole Patching- W Orange Grove Rd,- KN | NOPROBLEM | 2024-02-09 11:09
2024-02-04 15:13 | 24011724 | NEQ Pothole Patching-5545 E Paseo Cimarron, | RESOLVED | 2024-02-13 06:21
2024-02-04 15:24 | 24011725 | NEQ Pothole Patching-5699 E Paseo Cimarron, | RESOLVED | 2024-02-13 06:21
2024-02-04 16:59 | 24011727 | NWQ Pothole Patching-7403 N Camino de la Tierra | RESOLVED | 2024-02-13 05:56
2024-02-04 19:15 | 24011728 | NWQ Pothole Patching-Roller Coaster/Sunset | RESOLVED | 2024-02-21 16:01
2024-02-05 05:33 | 24011732 | SEQ Pothole Patching---470 S Harrison Rd | RESOLVED | 2024-02-14 10:21
2024-02-05 08:29 | 24011755 | SEQ Pothole Patching---9298 S Rita Rd | REFERRED | 2024-02-12 15:03
2024-02-05 08:34 | 24011757 | NWQ Pothole Patching-W Linda Vista Blvd | NOPROBLEM | 2024-02-20 15:00
2024-02-05 08:38 | 24011760 | NWQ Pothole Patching--9899 W Rudasill Rd | RESOLVED | 2024-02-15 05:46
2024-02-05 09:19 | 24011773 | NWQ Pothole Patching-W Ina rd | NOPROBLEM | 2024-02-12 15:19
2024-02-05 09:32 | 24011777 | NWQ Pothole Patching-Camino Del Fierro | RESOLVED | 2024-02-26 15:05
2024-02-05 09:35 | 24011778 | NEQ Pothole Patching-E Sunrise Dr & N Hacienda del Sol Rd | RESOLVED | 2024-02-12 06:22
2024-02-05 10:12 | 24011783 | NEQ Pothole Patching- S Houghton rd | REFERRED | 2024-02-12 15:10
2024-02-05 11:02 | 24011795 | MSQ Pothole Patching-3788 E Golder Ranch Dr & Twin Lakes | INPROG
2024-02-05 11:04 | 24011797 | MSQ Pothole Patching-3699 E Golder Ranch Dr | RESOLVED | 2024-02-12 09:06
2024-02-05 11:27 | 24011805 | SWQ Pothole Patching - S Cherokee Ln | RESOLVED | 2024-02-28 05:50
2024-02-05 12:07 | 24011811 | SEQ Pothole Patching--16698 S Old Sonoita Hwy | INPROG
2024-02-05 12:18 | 24011814 | NEQ Pothole Patching-E Cloud Rd | RESOLVED | 2024-02-26 06:21
2024-02-05 12:42 | 24011816 | SWQ Pothole Patching--371 E Placita Idilio | RESOLVED | 2024-02-06 15:22
2024-02-05 13:04 | 24011818 | NEQ Pothole Patching-N Tanque Verde Loop Rd- MC | TRANSFER
2024-02-05 13:36 | 24011819 | NEQ Pothole Patching-5760 N Chieftan Tr | RESOLVED | 2024-02-26 06:43
2024-02-05 14:05 | 24011827 | SEQ Pothole Patching-Vail View | RESOLVED | 2024-02-14 10:21
2024-02-05 17:13 | 24011848 | NWQ Pothole Patching-7343 N Camino de la Tierra | RESOLVED | 2024-02-13 05:56
2024-02-05 18:45 | 24011850 | SWQ Pothole Patching - W Pima Mine Rd | RESOLVED | 2024-02-22 09:12
2024-02-05 19:56 | 24011853 | NEQ Pothole Patching - 11121 E Michelle Ln | RESOLVED | 2024-02-27 06:01
2024-02-06 05:22 | 24011856 | NEQ Pothole Patching - 4410 N Sabino Canyon | RESOLVED | 2024-02-14 06:22
2024-02-06 07:35 | 24011861 | NWQ Pothole Patching -13263–13283 N Como Dr, | RESOLVED | 2024-02-26 07:04
2024-02-06 07:55 | 24011867 | SWQ Pothole Patching---9013 S Sierrita Mountain Rd | REFERRED | 2024-03-01 16:51
2024-02-06 08:20 | 24011872 | SWQ Pothole Patching-- 300 W Esperanza Blvd & N La Canada Dr | RESOLVED | 2024-02-06 15:08
2024-02-06 08:27 | 24011873 | NEQ Pothole Patching - N Hillcrest Dr @ River Rd | RESOLVED | 2024-02-27 06:06
2024-02-06 08:35 | 24011876 | NWQ Pothole Patching -N El Tovar Ave & W Garnette St, | RESOLVED | 2024-02-06 14:50
2024-02-06 09:29 | 24011880 | SWQ Pothole Patching - S Cherokee Ln | RESOLVED | 2024-02-28 05:50
2024-02-06 09:31 | 24011881 | SWQ Pothole Patching - W Scotland St | RESOLVED | 2024-02-28 05:50
2024-02-06 11:31 | 24011897 | SEQ Pothole Patching -E Andrada Rd & S Houghton Rd CJB | TRANSFER
2024-02-06 13:58 | 24011909 | SEQ Pothole Patching -3565-3685 S Old Spanish Trl | RESOLVED | 2024-02-14 10:22
2024-02-06 14:10 | 24011910 | SEQ Pothole Patching -N Paseo de Golf & E Placita Idilio | RESOLVED | 2024-02-07 06:25
2024-02-06 14:38 | 24011915 | NEQ Pothole Patching - 3800-3998 N Sutton Ln | RESOLVED | 2024-02-14 06:22
2024-02-06 19:26 | 24011936 | NWQ Pothole Patching - 12761 N Carbine Rd | RESOLVED | 2024-02-26 15:31
2024-02-06 21:02 | 24011937 | NWQ Pothole Patching - 7450 N Fortuna Pl | RESOLVED | 2024-02-09 07:03
2024-02-06 21:04 | 24011938 | NWQ Pothole Patching - 7401 N Mowry Pl | WOCREATED
2024-02-06 21:45 | 24011939 | NEQ Pothole Patching - Sunrise @ Hacienda Del Sol | RESOLVED | 2024-02-12 06:22
2024-02-07 09:53 | 24011972 | NWQ Pothole Patching -W Magee Rd | WOCREATED
2024-02-07 13:19 | 24012000 | NEQ Pothole Patching -9300-9408 E Walnut Tree Cir | NOPROBLEM | 2024-02-23 16:03
2024-02-07 15:14 | 24012016 | SEQ Pothole Patching -2905-3057 S Houghton Rd, | REFERRED | 2024-02-08 11:56
2024-02-07 15:56 | 24012018 | SEQ Pothole Patching -3902 East Drexel Road,- KN | NOPROBLEM | 2024-02-27 15:15
2024-02-07 17:49 | 24012024 | SWQ Pothole Patching - 6500 S Victor Dr | PRIVPROB | 2024-02-22 13:09
2024-02-07 18:14 | 24012026 | NEQ Pothole Patching -Bonanza @ Fort Lowell | RESOLVED | 2024-02-26 06:33
2024-02-07 18:42 | 24012027 | Pothole Patching -Drexel and Oak Tree | REFERRED | 2024-02-08 11:34
2024-02-07 19:17 | 24012028 | SEQ Pothole Patching - E Valencia @ S Wilmot | REFERRED | 2024-02-08 11:38
2024-02-07 20:20 | 24012029 | SWQ Pothole Patching - 7401 Calle Sevilla | PRIVPROB | 2024-02-23 15:56
2024-02-07 20:38 | 24012030 | SWQ Pothole Patching 6570 S Victor CJB | CLOSED
2024-02-07 20:53 | 24012031 | SWQ Pothole patching--7400 W Calle Castile | ASSIGNED
2024-02-08 08:04 | 24012042 | NEQ Swan and Sunrise - Potholes | RESOLVED | 2024-02-12 05:44
2024-02-08 08:07 | 24012043 | Pothole Patching -S Houghton Rd & E Andrada Rd | REFERRED | 2024-02-08 16:31
2024-02-08 08:45 | 24012048 | NWQ Pothole Patching -N La Cholla Blvd & W Sunset Rd | RESOLVED | 2024-02-21 16:01
2024-02-08 08:59 | 24012053 | NWQ Pothole Patching -5500-5568 N Silverbell Rd | RESOLVED | 2024-02-13 07:40
2024-02-08 09:12 | 24012057 | NEQ Pothole Patching -5789–5801 E Paseo Cimarron, | RESOLVED | 2024-02-13 06:21
2024-02-08 09:20 | 24012058 | NWQ Pothole Patching - 3700 E Golder Ranch Rd | WOCREATED
2024-02-08 09:31 | 24012060 | Pothole Patching Mead Rd | PENDING
2024-02-08 09:35 | 24012061 | NEQ Pothole Patching -3321 N Chapel Ave | RESOLVED | 2024-02-28 06:33
2024-02-08 10:10 | 24012065 | NEQ Pothole Patching -4700-4798 N Supai Pl | RESOLVED | 2024-02-27 09:53
2024-02-08 10:29 | 24012067 | SEQ Pothole Patching -625-667 E Whitehouse Canyon Rd | RESOLVED | 2024-02-21 05:57
2024-02-08 11:09 | 24012072 | SEQ Pothole Patching -S Old Sonoita Hwy | INPROG
2024-02-08 11:36 | 24012074 | SEQ Pothole Patching -6100 S Wilmot Rd | REFERRED | 2024-02-23 15:54
2024-02-08 11:52 | 24012078 | MSQ Pothole Patching -3285-3319 E Golder Ranch Dr, | RESOLVED | 2024-02-12 09:06
2024-02-08 11:57 | 24012079 | NWQ Pothole Patching -12950 West Sweetwater Drive | WOCREATED
2024-02-08 12:35 | 24012087 | SEQ Pothole Patching -14508-16698 S Old Sonoita Hwy, | INPROG
2024-02-08 12:42 | 24012089 | SEQ Pothole Patching -14508-16698 S Old Sonoita Hwy, | INPROG
2024-02-08 12:44 | 24012090 | SEQ Pothole Patching -601-699 E Camino Aurelia, | RESOLVED | 2024-02-26 06:38
2024-02-08 14:16 | 24012100 | SEQ Pothole Patching - S Contractors Wy @ Illinois | RESOLVED | 2024-02-14 10:21
2024-02-08 15:04 | 24012105 | NEQ Pothole Patching - N Sutton Ln | RESOLVED | 2024-02-14 06:22
2024-02-08 15:50 | 24012106 | NWQ Pothole Patching -W Hardy Rd, | RESOLVED | 2024-02-29 06:21
2024-02-08 16:53 | 24012110 | SEQ Pothole Patching -12877-12891 E Colossal Cave Rd, | RESOLVED | 2024-02-14 10:22
2024-02-08 17:07 | 24012111 | SEQ Pothole Patching -S Houghton Rd | REFERRED | 2024-02-23 15:52
2024-02-09 06:21 | 24012114 | SEQ Pothole Patching -14508-16698 S Old Sonoita Hwy- MC | TRANSFER
2024-02-09 06:44 | 24012116 | NEQ Pothole Patching -7667-7699 E Cloud Rd | RESOLVED | 2024-02-26 06:21
2024-02-09 07:44 | 24012117 | NWQ Pothole Patching -4419 N Flowing Wells Rd | RESOLVED | 2024-02-29 07:20
2024-02-09 10:36 | 24012136 | MSQ Pothole Patching -3285-3319 E Golder Ranch Dr | INPROG
2024-02-09 10:44 | 24012138 | SEQ Pothole Patching - 3716–3738 E Alvord Rd | REFERRED | 2024-02-20 14:56
2024-02-09 11:46 | 24012155 | NWQ Pothole Patching -W Overton Rd & N La Cholla Blvd, | RESOLVED | 2024-02-14 05:46
2024-02-09 11:57 | 24012158 | NWQ Pothole Patching -3609 W Camino De Talia, | WOCREATED
2024-02-09 12:03 | 24012159 | NWQ Pothole Patching -3625 W Camino De Caliope, | WOCREATED
2024-02-09 12:47 | 24012161 | SEQ Pothole Patching -14106-14122 E Colossal Cave Rd, | RESOLVED | 2024-02-21 15:54
2024-02-09 13:53 | 24012168 | SWQ Pothole Patching -5950 S Cardinal Ave, | RESOLVED | 2024-02-09 15:04
2024-02-09 16:19 | 24012187 | SWQ Pothole Patching- 6600-7000 -S Wade Rd | RESOLVED | 2024-02-15 15:12
2024-02-09 16:51 | 24012188 | MSQ Pothole Patching- E Golder Ranch dr | INPROG
2024-02-09 16:54 | 24012189 | SWQ Pothole Patching--4410 South Camino De Oeste, | RESOLVED | 2024-02-13 15:21
2024-02-09 17:02 | 24012190 | NWQ Pothole Patching-W River rd | RESOLVED | 2024-02-26 06:10
2024-02-09 17:13 | 24012192 | SEQ Pothole Patching-Old Nogales Hwy | INPROG
2024-02-09 17:21 | 24012193 | SWQ Pothole Patching - S Paseo Don Juan | RESOLVED | 2024-02-21 08:13
2024-02-09 20:32 | 24012194 | NWQ Pothole Patching--5498 N Silverbell Rd | RESOLVED | 2024-02-13 07:40
2024-02-09 22:18 | 24012196 | SEQ Pothole Patching--598 E Camino Aurelia | RESOLVED | 2024-02-26 06:38
2024-02-10 11:06 | 24012198 | NWQ Pothole Patching ---5568 N Silverbell Rd | RESOLVED | 2024-02-13 07:40
2024-02-10 13:15 | 24012199 | SEQ Pothole Patching---14104 E Colossal Cave Rd | RESOLVED | 2024-02-21 15:54
2024-02-10 14:07 | 24012200 | SWQ Pothole Patching - S Avenida Haley | RESOLVED | 2024-02-26 14:28
2024-02-10 14:30 | 24012202 | SEQ Pothole Patching-13699 S Houghton Rd | REFERRED | 2024-02-15 14:14
2024-02-10 16:29 | 24012204 | NEQ Pothole Patching--2564 N Sabino Canyon Rd @ Tanque Verde | RESOLVED | 2024-02-26 06:44
2024-02-10 21:07 | 24012207 | NWQ Pothole Patching--13499 N Derringer Rd, | RESOLVED | 2024-02-21 16:24
2024-02-10 22:12 | 24012208 | NWQ Pothole Patching -- W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-10 22:14 | 24012209 | NWQ Pothole Patching -- W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-11 06:33 | 24012210 | SEQ Pothole Patching - 4650 S Palo Verde Rd | RESOLVED | 2024-02-14 10:21
2024-02-11 06:35 | 24012211 | SEQ Pothole Patching - Country Club @ Benson Hy | REFERRED | 2024-02-20 14:28
2024-02-11 06:57 | 24012212 | SEQ Pothole Patching - S Palo Verde @ Irvington | REFERRED | 2024-02-20 14:25
2024-02-11 11:11 | 24012213 | NWQ Pothole Patching-N Kain Ave | RESOLVED | 2024-02-20 16:54
2024-02-11 11:23 | 24012214 | SEQ Pothole Patching-- S Houghton | REFERRED | 2024-02-12 14:49
2024-02-11 12:09 | 24012217 | NWQ Pothole Patching -3150 W Lobo Rd | WOCREATED
2024-02-11 12:13 | 24012218 | SEQ Pothole Patching--598 E Camino Aurelia | RESOLVED | 2024-02-26 06:38
2024-02-11 12:17 | 24012219 | SEQ Pothole Patching--598 E Camino Aurelia | RESOLVED | 2024-02-26 06:38
2024-02-11 12:18 | 24012220 | NWQ Pothole Patching--4199 W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-11 12:20 | 24012221 | NWQ Pothole Patching--3899 W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-11 12:21 | 24012222 | SEQ Pothole Patching--598 E Camino Aurelia | RESOLVED | 2024-02-26 06:38
2024-02-11 12:23 | 24012223 | NWQ Pothole Patching-W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-11 12:30 | 24012224 | NWQ Pothole Patching Tangerine | REFERRED | 2024-02-20 14:23
2024-02-11 12:54 | 24012226 | NWQ Pothole Patching-N La Cholla Blvd | RESOLVED | 2024-02-22 07:07
2024-02-11 13:53 | 24012228 | NEQ Pothole Patching--7598 E Cloud Rd | RESOLVED | 2024-02-26 06:21
2024-02-11 18:04 | 24012230 | NWQ Pothole Patching-–5448 N Willow Thicket Way | WOCREATED
2024-02-11 18:05 | 24012231 | NWQ Pothole Patching-5401 N Willow Thicket Way | INPROG
2024-02-11 18:05 | 24012232 | NWQ Pothole Patching-–1998 W Alder Grove Dr | INPROG
2024-02-11 19:43 | 24012233 | SEQ Pothole Patching--598 E Camino Aurelia | RESOLVED | 2024-02-26 06:38
2024-02-11 23:13 | 24012234 | SEQ Pothole Patching-S Palo Verde Rd & E Ajo Way | WOCREATED
2024-02-12 07:34 | 24012242 | SEQ Pothole Patching - 3701 S old Spanish Tr | RESOLVED | 2024-02-14 10:22
2024-02-12 07:54 | 24012246 | SEQ Pothole Patching - S Rex @ Drexel | RESOLVED | 2024-02-29 07:55
2024-02-12 08:16 | 24012254 | SEQ Pothole Patching-S Contractors Way & E Illinois St, | RESOLVED | 2024-02-14 10:21
2024-02-12 08:36 | 24012258 | SEQ Pothole Patching-S Houghton Rd | REFERRED | 2024-02-12 14:48
2024-02-12 09:05 | 24012265 | NWQ Pothole Patching-4151 W El Camino Del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-12 09:08 | 24012266 | NWQ Pothole Patching-4151 West El Camino Del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-12 09:51 | 24012273 | NWQ Pothole Patching--5471 N Silverbell Rd | RESOLVED | 2024-02-13 07:40
2024-02-12 09:51 | 24012274 | SEQ Pothole Patching-S Contractors Way | RESOLVED | 2024-02-14 10:21
2024-02-12 10:14 | 24012281 | SEQ Pothole Patching--12875 E Colossal Cave Rd | RESOLVED | 2024-02-14 10:22
2024-02-12 10:16 | 24012282 | SEQ Pothole Patching-S Camino Loma Alta | RESOLVED | 2024-02-21 15:53
2024-02-12 10:22 | 24012285 | SEQ Pothole Patching--12942 E Colossal Cave Rd | RESOLVED | 2024-02-14 10:22
2024-02-12 10:23 | 24012286 | SEQ Pothole Patching--12910 E Colossal Cave Rd | RESOLVED | 2024-02-14 10:22
2024-02-12 10:25 | 24012287 | SEQ Pothole Patching-S Houghton Rd, | REFERRED | 2024-02-15 11:04
2024-02-12 10:34 | 24012289 | SEQ Pothole Patching-S Contractors Way | RESOLVED | 2024-02-14 10:21
2024-02-12 10:51 | 24012293 | SEQ Pothole Patching-831 S Willis Ave | RESOLVED | 2024-02-20 08:03
2024-02-12 10:51 | 24012294 | SEQ Pothole Patching-S Contractors Way | RESOLVED | 2024-02-14 10:21
2024-02-12 11:08 | 24012296 | SWQ Pothole Patching-- 6600 S Wade Rd & S Camino Verde | RESOLVED | 2024-02-15 14:48
2024-02-12 11:27 | 24012298 | SEQ Pothole Patching-12936 E Douglas Camp Spring Dr, | RESOLVED | 2024-02-21 15:54
2024-02-12 11:44 | 24012300 | SEQ Pothole Patching-S Contractors Way | RESOLVED | 2024-02-14 10:21
2024-02-12 11:50 | 24012303 | SEQ Pothole Patching-S Houghton Rd- KN | REFERRED | 2024-02-12 14:29
2024-02-12 12:03 | 24012305 | NEQ Pothole Patching-1241 East Calle De La Cabra | RESOLVED | 2024-02-29 15:05
2024-02-12 12:11 | 24012308 | SEQ Pothole Patching--16983 S Old Sonoita Hwy | INPROG
2024-02-12 13:27 | 24012315 | NEQ Pothole Patching--6725 N Skyway Rd | RESOLVED | 2024-02-29 13:07
2024-02-12 13:44 | 24012317 | SEQ Pothole Patching - Old Spanish Tr @ Escalante | RESOLVED | 2024-02-21 15:52
2024-02-12 14:15 | 24012319 | NEQ Pothole Patching -E Cloud Rd, | RESOLVED | 2024-02-26 06:21
2024-02-12 14:48 | 24012321 | MSQ Pothole Patching-E Golder Ranch Dr | INPROG
2024-02-12 15:55 | 24012328 | NWQ Pothole Patching--12598 W Rudasill Rd | RESOLVED | 2024-02-15 05:46
2024-02-12 16:01 | 24012329 | NWQ Pothole Patching--12633 W Rudasill Rd | RESOLVED | 2024-02-15 05:46
2024-02-12 16:08 | 24012332 | SEQ Pothole Patching -13303 East Colossal Cave Road | RESOLVED | 2024-02-14 10:22
2024-02-12 16:09 | 24012334 | SEQ Pothole Patching -12951-12951 E Colossal Cave Rd, | RESOLVED | 2024-02-14 10:22
2024-02-12 16:11 | 24012335 | SEQ Pothole Patching -13712-13768 E Colossal Cave Rd, | RESOLVED | 2024-02-14 10:22
2024-02-12 16:12 | 24012336 | NEQ Pothole Patching -N Sabino Canyon Rd & E Tanque Verde Rd | RESOLVED | 2024-02-26 06:44
2024-02-12 16:15 | 24012337 | SEQ Pothole Patching -Old Spanish Tr north of Escalante | RESOLVED | 2024-02-21 15:52
2024-02-12 16:23 | 24012340 | NEQ Pothole Patching -E Cloud Rd & N Sabino Canyon Rd | RESOLVED | 2024-02-26 06:21
2024-02-12 16:44 | 24012342 | NEQ Pothole Patching -12510 East Gold Dust Drive, | RESOLVED | 2024-02-14 10:00
2024-02-12 16:49 | 24012343 | NWQ Pothole Patching- N Silverbell Rd, | RESOLVED | 2024-02-14 10:46
2024-02-12 16:58 | 24012344 | SWQ Pothole Patching - W Drexel Rd | RESOLVED | 2024-02-26 07:24
2024-02-12 17:03 | 24012345 | SEQ Pothole Patching -601-699 E Camino Aurelia, | RESOLVED | 2024-02-26 06:38
2024-02-12 17:26 | 24012348 | NEQ Pothole Patching-E Roger Rd | REFERRED | 2024-02-20 14:46
2024-02-12 17:44 | 24012349 | NEQ Pothole Patching -1535 East Big Rock Road, OV | TRANSFER
2024-02-12 20:09 | 24012350 | SEQ Pothole Patching -S Houghton Rd, | REFERRED | 2024-02-15 11:06
2024-02-12 20:44 | 24012351 | NEQ Pothole Patching -3563-3595 E Sunrise Dr, | RESOLVED | 2024-02-29 13:18
2024-02-12 20:55 | 24012352 | NEQ Pothole Patching -3563-3595 E Sunrise Dr | RESOLVED | 2024-02-29 13:18
2024-02-12 21:02 | 24012353 | NWQ Pothole Patching -N La Cholla Blvd, | RESOLVED | 2024-02-22 07:07
2024-02-12 21:03 | 24012354 | NWQ Pothole Patching-N La Cholla Blvd | RESOLVED | 2024-02-22 07:07
2024-02-12 21:19 | 24012355 | NWQ Pothole Patching-W Ruthrauff Rd | INPROG
2024-02-12 21:22 | 24012356 | NWQ Pothole Patching-N Fellows Ave & W Ruthrauff Rd | RESOLVED | 2024-02-29 06:17
2024-02-12 21:25 | 24012357 | NWQ Pothole Patching -N La Cholla Blvd & W Noreen St | RESOLVED | 2024-02-22 07:07
2024-02-12 21:30 | 24012358 | NWQ Pothole Patching -5400-5474 N La Cholla Blvd | RESOLVED | 2024-02-22 07:07
2024-02-12 21:34 | 24012359 | NWQ Pothole Patching -5400 North La Cholla Boulevard | RESOLVED | 2024-02-22 07:07
2024-02-12 21:54 | 24012360 | NWQ Pothole Patching -3700-3748 W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-12 22:00 | 24012361 | NWQ Pothole Patching -4601-4699 W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-12 22:29 | 24012362 | NWQ Pothole Patching -- W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-12 22:43 | 24012363 | NWQ Pothole Patching -4301-4599 W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-12 22:45 | 24012364 | NWQ Pothole Patching -3900-3998 W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-12 22:51 | 24012365 | NWQ Pothole Patching -4063-4099 W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-12 22:56 | 24012366 | NWQ Pothole Patching--4063-4099 W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-12 22:58 | 24012367 | NWQ Pothole Patching--4063-4099 W El Camino del Cerro | RESOLVED | 2024-02-15 06:23
2024-02-13 05:26 | 24012369 | SWQ Pothole Patching - W Ocotillo Ranch Rd | RESOLVED | 2024-02-26 14:28
2024-02-13 05:27 | 24012370 | SWQ Pothole Patching - W Calle Uno | RESOLVED | 2024-02-26 14:29
2024-02-13 06:07 | 24012376 | NWQ Pothole Patching -N Camino de la Tierra | WOCREATED
2024-02-13 06:59 | 24012378 | NEQ Pothole Patching -N Sabino Canyon south of Snyder | RESOLVED | 2024-02-15 13:57
2024-02-13 07:29 | 24012380 | SEQ Pothole Patching -7272-7328 S Camino Mirlo | RESOLVED | 2024-02-21 15:53
2024-02-13 07:46 | 24012381 | NWQ Pothole Patching -2789–2799 W Curtis Rd | WOCREATED
2024-02-13 08:18 | 24012383 | SEQ P{othole Patching - 13701 S Houghton Rd | REFERRED | 2024-02-23 15:45
2024-02-13 08:23 | 24012384 | SEQ Pothole Patching - S Houghton - KN | TRANSFER
2024-02-13 08:25 | 24012385 | NEQ Pothole Patching - E Broadway | RESOLVED | 2024-02-29 13:07
2024-02-13 09:57 | 24012404 | NWQ Pothole Patching -N La Cholla Blvd & W Oracle Jaynes Station OV | TRANSFER
2024-02-13 10:49 | 24012414 | SWQ Pothole Patching -4701–4745 W Calle Don Miguel, | RESOLVED | 2024-02-14 10:08
2024-02-13 10:59 | 24012416 | SWQ Pothole Patching - S San Joaquin Rd | RESOLVED | 2024-02-20 08:01
2024-02-13 13:08 | 24012431 | NWQ Pothole Patching -4200-4308 N Plum Ave, | WOCREATED
2024-02-13 13:20 | 24012433 | SWQ Pothole Patching - W Pima Mine Rd | RESOLVED | 2024-02-22 09:12
2024-02-13 13:52 | 24012438 | SEQ Pothole Patching -E Sahuarita Rd & S Houghton Rd | REFERRED | 2024-02-13 15:56
2024-02-13 14:10 | 24012442 | NWQ Pothole Patching -2501 West Orange Grove Road | RESOLVED | 2024-02-21 16:08
2024-02-13 14:39 | 24012446 | NWQ Pothole Patching -4621-4743 N Highway Dr | NOPROBLEM | 2024-02-22 11:36
2024-02-13 14:53 | 24012447 | NEQ Pothole Patching -4043 N Harrison Rd, | RESOLVED | 2024-02-14 10:30
2024-02-13 14:58 | 24012449 | NWQ Pothole Patching -1142–1164 W Magee Rd, | WOCREATED
2024-02-13 15:02 | 24012450 | NWQ Pothole Patching -4340 West Sweetwater Drive | WOCREATED
2024-02-13 15:03 | 24012451 | SWQ Pothole Patching - S Cherokee Ln | RESOLVED | 2024-02-28 05:50
2024-02-13 15:09 | 24012454 | NWQ Pothole Patching -1312–1398 W Magee Rd, | INPROG
2024-02-13 15:09 | 24012455 | NWQ Pothole Patching -4340 West Sweetwater Drive, | INPROG
2024-02-13 15:31 | 24012459 | SEQ Pothole Patching -S Houghton Rd, | REFERRED | 2024-02-13 15:56
2024-02-13 15:32 | 24012460 | NEQ Pothole Patching -4081 N Harrison Rd | RESOLVED | 2024-02-14 10:30
2024-02-13 16:40 | 24012462 | SWQ Pothole Patching - S Cherokee Ln | RESOLVED | 2024-02-28 05:50
2024-02-13 18:00 | 24012465 | SEQ Pothole Patching - S Houghton north of Andrada Rd | REFERRED | 2024-02-15 11:02
2024-02-13 20:50 | 24012471 | SEQ Pothole Patching | REFERRED | 2024-02-15 11:01
2024-02-14 05:28 | 24012473 | SWQ Pothole Patching - W Pima Mine Rd | RESOLVED | 2024-02-22 09:12
2024-02-14 06:28 | 24012474 | SWQ Pothole Patching---12199 W Snyder Hill Rd | REFERRED | 2024-02-23 15:08
2024-02-14 07:48 | 24012479 | SEQ Pothole Patching-S Houghton Rd | REFERRED | 2024-02-15 10:59
2024-02-14 08:09 | 24012480 | SEQ Pothole Patching-S Houghton Rd | REFERRED | 2024-02-15 10:57
2024-02-14 08:23 | 24012485 | NEQ Pothole Patching - 5789 E Paseo Cimarron | WOCREATED
2024-02-14 10:41 | 24012504 | NWQ Pothole Patching - N Aspen @ Lemon | WOCREATED
2024-02-14 10:43 | 24012505 | NWQ Pothole Patching - W Pomona @ Cypress St | WOCREATED
2024-02-14 10:50 | 24012506 | NWQ Pothole Patching -1610 West Sage Street | WOCREATED
2024-02-14 11:38 | 24012512 | SEQ Pothole Patching--13924 S Old Sonoita Hwy | INPROG
2024-02-14 11:51 | 24012515 | SWQ Pothole Patching - W Bilby Rd | RESOLVED | 2024-02-20 07:06
2024-02-14 11:55 | 24012517 | SWQ Pothole Patching--6100-6200 S Westover Ave | RESOLVED | 2024-02-29 11:05
2024-02-14 12:33 | 24012525 | NEQ Pothole Patching-E Cloud Rd | RESOLVED | 2024-02-26 06:21
2024-02-14 13:15 | 24012529 | SWQ Pothole Patching - S Westover Ave | RESOLVED | 2024-02-28 05:50
2024-02-14 13:27 | 24012531 | SEQ Pothole Patching -10119 South Green Driv | RESOLVED | 2024-02-29 07:56
2024-02-14 13:33 | 24012534 | SWQ Pothole Patching -5877–5899 S Camino Verde | RESOLVED | 2024-02-16 07:02
2024-02-14 15:00 | 24012540 | SEQ Pothole Patching -E Andrada Rd & S Houghton Rd, | REFERRED | 2024-02-15 10:52
2024-02-14 15:15 | 24012543 | SEQ Pothole Patching-S Houghton Rd | REFERRED | 2024-02-15 10:50
2024-02-14 15:45 | 24012545 | SEQ Pothole Patching-S Houghton Rd OV | REFERRED | 2024-02-15 10:49
2024-02-14 15:46 | 24012546 | SEQ Pothole Patching-S Houghton Rd | REFERRED | 2024-02-15 12:46
2024-02-14 16:24 | 24012550 | NWQ Pothole Patching - W Panorama Rd | WOCREATED
2024-02-14 16:49 | 24012552 | SEQ Pothole Patching - 532 N Fairhaven Dr | WOCREATED
2024-02-14 19:39 | 24012555 | SEQ Pothole Patching - S Houghton south of Andrada High | REFERRED | 2024-02-15 10:47
2024-02-14 19:42 | 24012556 | SEQ Pothole Patching - 10355 E Pantano Tr | PRIVPROB | 2024-02-22 11:28
2024-02-14 19:46 | 24012557 | SEQ Pothole Patching-S Houghton Rd | REFERRED | 2024-02-15 10:43
2024-02-14 20:17 | 24012558 | NWQ Pothole Patching -6522-6572 N Silverbell Rd | RESOLVED | 2024-02-20 05:42
2024-02-14 20:23 | 24012559 | NWQ Pothole Patching -2537-2539 W Orange Grove Rd | RESOLVED | 2024-02-21 16:08
2024-02-14 20:26 | 24012560 | NWQ Pothole Patching -N La Oesta Ave & W Magee Rd | WOCREATED
2024-02-14 20:28 | 24012561 | SEQ Pothole Patching -S Houghton Rd | REFERRED | 2024-02-15 10:41
2024-02-14 20:29 | 24012562 | NWQ Pothole Patching -N La Canada Dr & W Magee Rd, | WOCREATED
2024-02-14 20:35 | 24012563 | SEQ Pothole Patching -S Houghton Rd | REFERRED | 2024-02-15 10:40
2024-02-14 20:35 | 24012564 | SEQ Pothole Patching -S Houghton Rd, | REFERRED | 2024-02-15 10:38
2024-02-15 02:16 | 24012566 | SEQ Pothole Patching -13701-13925 S Houghton Rd | REFERRED | 2024-02-15 10:37
2024-02-15 06:54 | 24012570 | NEQ Pothole Patching-E Tanque Verde Rd | RESOLVED | 2024-02-27 10:11
2024-02-15 07:18 | 24012571 | SWQ Pothole Patching-10716 S Sierrita Mountain Rd | REFERRED | 2024-02-22 12:12
2024-02-15 08:29 | 24012581 | SEQ Pothole Patching-S Houghton Rd | REFERRED | 2024-02-27 09:16
2024-02-15 08:52 | 24012582 | SEQ Pothole Patching-S Houghton Rd | REFERRED | 2024-02-21 08:17
2024-02-15 09:38 | 24012588 | NWQ Pothole Patching-6240 North Tula Lane OV | TRANSFER
2024-02-15 09:40 | 24012589 | NWQ Pothole Patching -900 West Panorama Road, | INPROG
2024-02-15 09:48 | 24012592 | NWQ Pothole Patching -N Panorama Cir & W Panorama Rd | INPROG
2024-02-15 10:27 | 24012598 | SWQ Pothole Patching - S Riveria Dr | RESOLVED | 2024-03-04 07:19
2024-02-15 11:04 | 24012603 | SEQ Pothole Patching-S Houghton Rd OV | REFERRED | 2024-02-16 10:04
2024-02-15 11:49 | 24012606 | SEQ Pothole Patching - S Contractors Wy @ Michigan | RESOLVED | 2024-02-22 06:10
2024-02-15 12:09 | 24012609 | NEQ Pothole Patching - 7600 E Cloud Rd | RESOLVED | 2024-02-26 06:21
2024-02-15 12:13 | 24012610 | NEQ Pothole Patching - 10641 E Deerfield Pl | RESOLVED | 2024-02-27 09:55
2024-02-15 12:56 | 24012614 | SEQ Pothole Patching -S Houghton Rd & E Andrada Rd, OV | REFERRED | 2024-02-16 09:51
2024-02-15 13:14 | 24012615 | SEQ Pothole Patching -11100–11150 E Timrod St, | PRIVPROB | 2024-02-23 12:37
2024-02-15 13:15 | 24012616 | SEQ Pothole Patching -11100–11150 E Timrod St, | PRIVPROB | 2024-02-23 12:37
2024-02-15 13:16 | 24012617 | SEQ Pothole Patching -11100–11150 E Timrod St | PRIVPROB | 2024-02-23 12:36
2024-02-15 13:30 | 24012618 | NEQ Pothole Patching -10650 East Sundance Circle | RESOLVED | 2024-02-29 13:07
2024-02-15 14:38 | 24012624 | NWQ Pothole Patching-10098 W Rudasill Rd | INPROG
2024-02-15 14:48 | 24012629 | SWQ Pothole Patching - W Pima Mine Rd | RESOLVED | 2024-02-22 09:12
2024-02-15 16:23 | 24012648 | SWQ Pothole Patching - W Milky Way Dr | RESOLVED | 2024-02-21 06:11
2024-02-15 16:59 | 24012656 | NWQ Pothole Patching -N Derringer Rd & W El Tiro Rd | RESOLVED | 2024-02-21 16:24
2024-02-15 19:50 | 24012657 | NEQ Pothole Patching -N Camino Sin Vacas and E Ina Rd- KN | TRANSFER
2024-02-16 09:10 | 24012676 | NEQ Pothole Patching - 13515 E Placita El Centeno | WOCREATED
2024-02-16 09:35 | 24012681 | NEQ Pothole Patching -N Wentworth Rd & E Tanque Verde Rd | RESOLVED | 2024-02-26 06:22
2024-02-16 09:40 | 24012682 | NEQ Pothole Patching -E Tanque Verde Rd & N Conestoga Ave OV | TRANSFER
2024-02-16 10:26 | 24012685 | NEQ Pothole Patching -E Camino de los Padres & N Skyway Rd | RESOLVED | 2024-02-29 13:07
2024-02-16 10:30 | 24012686 | SEQ Pothole Patching -4650 South Palo Verde Road, | NOPROBLEM | 2024-02-27 11:33
2024-02-16 11:56 | 24012694 | NWQ Pothole Patching -6141 W Rudasill Rd | WOCREATED
2024-02-16 13:21 | 24012700 | NWQ Pothole Patching -9802-9898 W Rudasill Rd, | INPROG
2024-02-16 13:28 | 24012702 | NWQ Pothole Patching-7341 N Ellison Dr | WOCREATED
2024-02-16 13:30 | 24012703 | NWQ Pothole Patching -7405 N Ellison Dr | INPROG
2024-02-16 13:38 | 24012704 | NWQ Pothole Patching -W Moore Rd & N Como Dr | RESOLVED | 2024-02-26 07:04
2024-02-16 14:08 | 24012714 | SWQ Pothole Patching - S Paisano Ave | RESOLVED | 2024-02-28 05:51
2024-02-16 16:10 | 24012729 | NEQ Pothole Patching - E Cloud Rd east of N Sabino Canyon | RESOLVED | 2024-02-26 06:21
2024-02-16 16:32 | 24012732 | SEQ Pothole Patching - Colossal Cave Rd @ Via Rancho Del Lago | RESOLVED | 2024-02-21 15:54
2024-02-16 16:39 | 24012734 | NWQ Pothole Patching-4399 N El Tovar Ave | RESOLVED | 2024-02-22 05:52
2024-02-16 19:42 | 24012741 | SEQ Pothole Patching - 3700 E Alvord | REFERRED | 2024-02-27 11:07
2024-02-17 10:14 | 24012743 | SEQ Pothole Patching - S Houghton Rd north of Andrada | REFERRED | 2024-02-23 13:56
2024-02-17 13:07 | 24012744 | SEQ Pothole Patching - S Houghton south of Andrada high school | REFERRED | 2024-02-23 13:52
2024-02-17 14:02 | 24012745 | NEQ Pothole Patching-N Supai Pl | RESOLVED | 2024-02-27 09:53
2024-02-17 14:13 | 24012746 | SEQ Pothole Patching - S alvernon Wy @ Benson Hy | REFERRED | 2024-02-27 11:00
2024-02-17 14:21 | 24012747 | NWQ Pothole Patching-W Gates Pass Rd & N Via Roma | RESOLVED | 2024-02-22 05:57
2024-02-17 14:31 | 24012748 | NWQ Pothole Patching-Sweetwater & Silverbell rd | WOCREATED
2024-02-17 14:54 | 24012749 | SWQ Pothole Patching--W Esperanza Blvd & S Paseo Seco | RESOLVED | 2024-02-23 14:43
2024-02-17 15:22 | 24012750 | NWQ Pothole Patching-5401 N Willow Thicket Way | INPROG
2024-02-17 17:06 | 24012753 | NEQ Pothole Patching - 6720 N Skyway | RESOLVED | 2024-02-29 13:07
2024-02-18 09:24 | 24012756 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-18 10:12 | 24012758 | SEQ Pothole Patching - S Catalina Av north of Benson Hy | WOCREATED
2024-02-18 16:02 | 24012763 | NEQ Pothole Patching - 5680 E Paseo Cimarron | INPROG
2024-02-18 16:23 | 24012764 | NEQ Pothole Patching - Camino Piedras @ Cloud Rd | RESOLVED | 2024-02-26 06:21
2024-02-18 16:27 | 24012765 | NEQ Pothole Patching- 5794 E Paseo Cimarron | INPROG
2024-02-18 16:30 | 24012766 | NEQ Pothole Patching - 5790 E Paseo Cimarron | INPROG
2024-02-18 16:36 | 24012767 | NEQ Pothole Patching - 5730 E Paseo Cimarron | INPROG
2024-02-18 17:51 | 24012768 | SEQ Pothole Patching - Rex @ Drexel | RESOLVED | 2024-02-29 07:55
2024-02-18 20:31 | 24012770 | NEQ Pothole Patching - 5601 N Paseo Ventoso | RESOLVED | 2024-02-26 06:43
2024-02-18 23:40 | 24012771 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-18 23:43 | 24012772 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-18 23:46 | 24012773 | NWQ Pothole Patching-W Moore Rd | RESOLVED | 2024-02-29 06:43
2024-02-18 23:48 | 24012774 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 07:28 | 24012775 | SEQ Pothole Patching-10901 S Distillery Canyon Spring Dr | RESOLVED | 2024-02-21 15:54
2024-02-19 08:36 | 24012776 | NWQ Pothole Patching Rurthrauff | RESOLVED | 2024-02-29 06:17
2024-02-19 08:37 | 24012777 | NWQ Pothole Patching--2423 W Ruthrauff Rd | RESOLVED | 2024-02-29 06:17
2024-02-19 08:39 | 24012778 | NWQ Pothole Patching-N La Cholla Blvd | RESOLVED | 2024-02-22 07:07
2024-02-19 08:42 | 24012779 | NWQ Pothole Patching-N La Cholla Blvd | RESOLVED | 2024-02-22 07:07
2024-02-19 09:12 | 24012780 | NEQ Pothole Patching - E cloud Rd east of Sabino Canyon | RESOLVED | 2024-02-26 06:21
2024-02-19 11:27 | 24012781 | NEQ Pothole Patching - 13225 E Placita Las Avenas | RESOLVED | 2024-02-29 13:07
2024-02-19 14:03 | 24012783 | SWQ Pothole Patching--W Irvington Pl & S Mission Rd | REFERRED | 2024-02-27 10:51
2024-02-19 15:15 | 24012785 | NEQ Pothole Patching--3599 N Wendell Rd | RESOLVED | 2024-02-29 13:07
2024-02-19 16:00 | 24012787 | NWQ Pothole Patching-Camino de Oeste | REFERRED | 2024-02-27 09:23
2024-02-19 17:46 | 24012789 | NWQ Pothole Patching-17002 W Moore Rd, | RESOLVED | 2024-02-29 06:43
2024-02-19 17:47 | 24012790 | NWQ Pothole Patching-17002 W Moore Rd, | RESOLVED | 2024-02-29 06:43
2024-02-19 17:49 | 24012791 | NWQ Pothole Patching-17002 W Moore Rd, | RESOLVED | 2024-02-29 06:43
2024-02-19 17:49 | 24012792 | NWQ Pothole Patching-17002 W Moore Rd, | RESOLVED | 2024-02-29 06:43
2024-02-19 17:50 | 24012793 | NWQ Pothole Patching-17002 W Moore Rd, | RESOLVED | 2024-02-29 06:43
2024-02-19 17:51 | 24012794 | NWQ Pothole Patching-Moore rd | RESOLVED | 2024-02-29 06:43
2024-02-19 17:52 | 24012795 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:53 | 24012796 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:54 | 24012797 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:56 | 24012798 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:56 | 24012800 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:57 | 24012799 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:58 | 24012803 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:58 | 24012802 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:58 | 24012801 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:58 | 24012804 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:58 | 24012805 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:59 | 24012806 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 17:59 | 24012807 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:00 | 24012808 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:00 | 24012809 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:00 | 24012810 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:01 | 24012811 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:01 | 24012812 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:01 | 24012813 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:02 | 24012814 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:02 | 24012815 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:03 | 24012816 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:03 | 24012817 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:03 | 24012818 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:04 | 24012819 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:04 | 24012820 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:04 | 24012821 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:05 | 24012822 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:05 | 24012823 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:05 | 24012824 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:06 | 24012825 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:06 | 24012826 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:07 | 24012827 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:07 | 24012828 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:08 | 24012829 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:08 | 24012830 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:08 | 24012831 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:09 | 24012832 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:09 | 24012833 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:09 | 24012834 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:09 | 24012835 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:10 | 24012836 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:10 | 24012837 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:10 | 24012838 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:11 | 24012839 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:11 | 24012840 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:11 | 24012841 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:12 | 24012843 | NWQ Pothole Patching-N Derringer Rd | INPROG
2024-02-19 18:12 | 24012842 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 18:14 | 24012844 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-19 19:41 | 24012845 | NWQ Pothole Patching-Ruthrauff rd | RESOLVED | 2024-02-29 06:17
2024-02-19 19:47 | 24012846 | NWQ Pothole Patching- 4200 W El Camino Del Cerro | RESOLVED | 2024-02-23 15:03
2024-02-19 19:52 | 24012847 | NWQ Pothole Patching- 4100 W El Camino Del Cerro | RESOLVED | 2024-02-23 15:18
2024-02-19 19:56 | 24012848 | NWQ Pothole Patching-W Ruthrauff Rd | RESOLVED | 2024-02-29 06:17
2024-02-19 20:11 | 24012849 | NWQ Pothole Patching- 2100 W Orange Grove Rd | RESOLVED | 2024-02-23 15:31
2024-02-19 20:13 | 24012850 | NWQ Pothole Patching--1923 W Orange Grove Rd, | RESOLVED | 2024-02-23 15:46
2024-02-19 21:23 | 24012851 | NWQ Pothole Patching Orange Grove & Corona | PRIVPROB | 2024-02-27 09:13
2024-02-20 07:24 | 24012866 | SEQ Pothole Patching--10566 S Swan Rd | RESOLVED | 2024-02-29 07:55
2024-02-20 07:58 | 24012876 | NWQ Pothole Patching-4824 N Jay Av | WOCREATED
2024-02-20 08:42 | 24012890 | NEQ Pothole Patching - N Skyway south of Chula Vista | RESOLVED | 2024-02-29 13:07
2024-02-20 09:40 | 24012896 | NEQ Pothole Patching - E Cloud Rd east of Sabino Canyon | RESOLVED | 2024-02-26 06:21
2024-02-20 09:45 | 24012897 | NEQ Pothole Patching-E Cloud Rd | RESOLVED | 2024-02-26 06:21
2024-02-20 10:40 | 24012904 | SEQ Pothole Patching-951 East Fenley Drive | WOCREATED
2024-02-20 10:44 | 24012905 | NWQ Pothole Patching-N Derringer Rd | RESOLVED | 2024-02-21 16:24
2024-02-20 10:45 | 24012907 | NEQ Pothole Patching--7798 E Cloud Rd | RESOLVED | 2024-02-26 06:21
2024-02-20 11:44 | 24012913 | NWQ Pothole Patching-10330 North Feldman Road | WOCREATED
2024-02-20 12:36 | 24012917 | SEQ Pothole Patching--10566 S Swan Rd | RESOLVED | 2024-02-29 07:55
2024-02-20 13:50 | 24012923 | NWQ Pothole Patching -3719 West Sunbright Drive | NOPROBLEM | 2024-03-01 08:39
2024-02-20 15:31 | 24012934 | NEQ Pothole Patching - Canyon Dr @ Rudasill | RESOLVED | 2024-02-29 12:57
2024-02-20 15:33 | 24012935 | NEQ Pothole Patching - Canyon Dr @ Roberta | RESOLVED | 2024-02-29 12:57
2024-02-20 18:22 | 24012943 | SEQ Pothole Paching - 10898 E rock Ridge Dr Vail OV | TRANSFER
2024-02-21 07:56 | 24012950 | NWQ Pothole Patching -N Blue Bonnet Rd & W Linda Vista Blvd | NOPROBLEM | 2024-02-28 11:28
2024-02-21 09:43 | 24012963 | SWQ Pothole Patching - S Sorrel Ln | RESOLVED | 2024-02-28 07:39
2024-02-21 10:39 | 24012976 | NWQ Pothole Patching-N La Cholla Blvd | WOCREATED
2024-02-21 10:40 | 24012977 | SWQ Pothole Patching--–5599 S Cardinal Ave | RESOLVED | 2024-02-22 05:50
2024-02-21 12:09 | 24012989 | SWQ Pothole Patching-- 3600 W Los Reales Rd | RESOLVED | 2024-02-22 05:31
2024-02-21 12:58 | 24012995 | SWQ Pothole Patching - W Delfina Dr | RESOLVED | 2024-02-28 07:40
2024-02-21 13:08 | 24012997 | NEQ Pothole Patching -3201-3399 N Bonanza Ave MC | TRANSFER
2024-02-21 13:10 | 24012998 | NEQ Pothole Patching -E Cloud rd | RESOLVED | 2024-02-26 06:21
2024-02-21 13:28 | 24013005 | NWQ Pothole Patching -N Camino de Oeste & W Linda Vista Blvd, OV | TRANSFER
2024-02-21 14:37 | 24013007 | SWQ Pothole Patching - 11800-12198 W Snyder Hill Rd, OV | TRANSFER
2024-02-21 14:42 | 24013008 | SWQ Pothole Patching - S Marstellar Rd | RESOLVED | 2024-02-29 08:49
2024-02-21 20:27 | 24013016 | NEQ Pothole Patching - 3601-3699 N White Pearl Ln | RESOLVED | 2024-02-29 13:07
2024-02-22 06:36 | 24013018 | SEQ Pothole Patching -14136-14164 E Old Spanish Tr | INPROG
2024-02-22 13:58 | 24013064 | NWQ Pothole Patching - 6180 N Sanders Rd | WOCREATED
2024-02-22 14:16 | 24013069 | NWQ Pothole Patching -W Placita Tampico- KN | TRANSFER
2024-02-22 14:52 | 24013077 | NEQ Pothole Patching -E Paseo de Beatriz, | RESOLVED | 2024-02-27 06:01
2024-02-22 15:46 | 24013085 | SWQ Pothole Patching -13436-13628 S Sierrita Mountain Rd, OV | TRANSFER
2024-02-22 17:55 | 24013089 | SEQ Pothole Patching -13722-13746 E Old Spanish Tr | WOCREATED
2024-02-23 07:44 | 24013098 | SWQ Pothole Patching -8561 S Sierrita Mountain Rd OV | CLOSED
2024-02-23 10:13 | 24013111 | NWQ Pothole Patching-W Cactus Canyon Pass | WOCREATED
2024-02-23 12:04 | 24013124 | SWQ Pothole Patching -S San Joaquin Rd - KN | NOPROBLEM | 2024-02-29 11:51
2024-02-23 12:09 | 24013126 | SWQ Pothole Patching -W Bopp Rd & S Leonard Ave | ASSIGNED
2024-02-23 14:59 | 24013142 | SWQ Pothole Patching -4081 South Leonard Avenue | ASSIGNED
2024-02-23 15:10 | 24013144 | NWQ Pothole Patching -6550 North Desert View Drive | INPROG
2024-02-23 18:36 | 24013148 | SWQ Pothole Patching---6904 S Camino Verde | RESOLVED | 2024-02-28 07:05
2024-02-24 06:32 | 24013149 | SWQ Pothole Patching--W Snyder Hill Rd OV | TRANSFER
2024-02-24 10:17 | 24013150 | NWQ Pothole Patching - 4201-4315 N Plum Av- KN | PRIVPROB | 2024-02-29 11:50
2024-02-24 17:26 | 24013153 | NEQ Pothole Patching - N Tomahawk Tr | RESOLVED | 2024-02-27 13:51
2024-02-25 08:47 | 24013154 | NWQ Pothole Patching - 4806- 4998 N Gold Av | RESOLVED | 2024-02-28 14:50
2024-02-25 12:54 | 24013156 | NWQ Pothole Patching-401 W Orange Grove Rd | INPROG
2024-02-25 13:03 | 24013157 | NWQ Pothole Patching - Orange Grove @ La Cholla | INPROG
2024-02-25 13:06 | 24013158 | NWQ Pothole Patching - Orange Grove @ La Cholla | WOCREATED
2024-02-26 08:06 | 24013169 | NWQ Pothole Patching - 2262 N Calle Narciso | WOCREATED
2024-02-26 08:21 | 24013173 | SEQ Pothole Patching - 9802 S Cactus Ln | WOCREATED
2024-02-26 08:32 | 24013176 | SWQ Pothole Patching---4599 W Tumacacori Dr | RESOLVED | 2024-02-28 08:11
2024-02-26 08:34 | 24013177 | NEQ Pothole Patching - Wentworth @ Tanque Verde wash- KN | REFERRED | 2024-02-26 15:28
2024-02-26 08:39 | 24013180 | NWQ Pothole Patching - 10700 N Portland Av | WOCREATED
2024-02-26 10:41 | 24013210 | SWQ Pothole Patching - W Park Rd | WOCREATED
2024-02-26 18:52 | 24013244 | SWQ Pothole Patching--14200 S Avenida Red Roan- KN | NOPROBLEM | 2024-02-29 11:50
2024-02-26 21:40 | 24013245 | NWQ Pothole Patching -W Magee Rd, | INPROG
2024-02-26 21:42 | 24013246 | NWQ Pothole Patching -9952-10024 N Pecos Way | RESOLVED | 2024-02-28 15:17
2024-02-26 21:46 | 24013247 | NWQ Pothole Patching - 7700 N Thornydale rd | RESOLVED | 2024-02-29 15:49
2024-02-27 06:24 | 24013251 | NWQ Pothole Patching - 4048 N Tutlte Av | RESOLVED | 2024-02-29 15:29
2024-02-27 06:57 | 24013253 | SEQ Pothole Patching-12900 E Douglas Camp Spring Dr | WOCREATED
2024-02-27 08:19 | 24013268 | NWQ Pothole Patching-W Elk Trl & N Anway Rd | PENDING
2024-02-27 09:42 | 24013278 | NWQ Pothole Patching- 9400 W Avra Valley Rd | RESOLVED | 2024-03-01 14:55
2024-02-27 11:26 | 24013290 | NWQ Pothole Patching -W El Camino del Cerro & N Silverbell Rd- KN | REFERRED | 2024-02-28 11:40
2024-02-27 12:01 | 24013292 | SWQ Pothole Patching--–8998 S Mission Rd | RESOLVED | 2024-02-28 08:20
2024-02-27 13:33 | 24013299 | SEQ Pothole Patching-S Houghton Rd | REFERRED | 2024-02-28 08:24
2024-02-27 13:55 | 24013305 | NWQ Pothole Patching- 11100 N Thornydale Rd & W Montgomery St | RESOLVED | 2024-02-28 15:04
2024-02-27 14:40 | 24013312 | NWQ Pothole Patching- 7300 N Leonardo da Vinci Way & W Wanda Vista Rd | WOCREATED
2024-02-27 16:04 | 24013317 | NWQ Pothole Patching- 8300 N Cerius Stravenue | RESOLVED | 2024-02-28 15:39
2024-02-27 16:57 | 24013327 | NEQ Pothole Patching - E Placita Las Avenas | RESOLVED | 2024-02-29 13:07
2024-02-27 19:54 | 24013329 | NEQ Pothole Patching--4799 N Tonalea Trl, | ASSIGNED
2024-02-27 22:42 | 24013330 | NEQ Pothole Patching - White Pearl Ln @ Prince Rd | RESOLVED | 2024-02-29 13:07
2024-02-27 22:44 | 24013331 | NEQ Pothole Patching - White Pearl Ln | RESOLVED | 2024-02-29 13:07
2024-02-28 09:05 | 24013343 | NWQ Pothole Patching -17545 West Marana Road, | PENDING
2024-02-28 11:53 | 24013363 | SEQ Pothole Patching-Rex Ave | RESOLVED | 2024-02-29 07:55
2024-02-28 13:46 | 24013376 | SEQ Pothole Patching-S Bryant Stravenue @ E Drexel | PENDING
2024-02-28 16:20 | 24013391 | NWQ Pothole Patching -N Camino del Fierro & W Overton Rd | ASSIGNED
2024-02-29 02:08 | 24013398 | NWQ Pothole Patching-7555 North La Cholla Boulevard, | REFERRED | 2024-03-01 15:27
2024-02-29 08:54 | 24013421 | NWQ Pothole Patching-N Plum Ave | INPROG
2024-02-29 12:37 | 24013433 | NWQ Pothole Patching- 4350 N Plum Ave | ASSIGNED
2024-02-29 13:50 | 24013443 | NWQ Pothole Patching--8927 N Camino del Fierro | ASSIGNED
2024-02-29 14:11 | 24013450 | NEQ Pothole Patching-N Camino Arco | ASSIGNED
2024-02-29 15:41 | 24013457 | NEQ Pothole Patching -4401 North Avenida Del Cazador, | ASSIGNED
2024-02-29 16:51 | 24013462 | SEQ Pothole Patching -E Sterling Canyon dr OV | TRANSFER
2024-02-29 18:54 | 24013469 | NEQ Pothole Patching -7198 E Cloud Rd | ASSIGNED
2024-02-29 18:57 | 24013470 | SWQ Pothole Patching -14200 S Avenida Red Roan | ASSIGNED
2024-03-01 08:24 | 24013485 | NEQ Pothole Patching -6661 North Skyway Road, | ASSIGNED
2024-03-01 10:54 | 24013504 | SWQ Pothole Patching -W Esperanza Blvd & S La Canada Dr, | PENDING
2024-03-01 14:26 | 24013519 | SWQ Pothole Patching -S Camino del Sol & W Camino Urbano | PENDING
2024-03-01 16:30 | 24013531 | NWQ Pothole Patching Cool Dr | ASSIGNED
2024-03-01 16:32 | 24013532 | NWQ Pothole Patching Panorama Rd | ASSIGNED
2024-03-01 16:44 | 24013534 | NWQ Pothole Patching Panorama Ln, Rd & CI | ASSIGNED

## Status Explanation
STATUS | Explanation
ASSIGNED | Maintenance Field Review
CLOSED | Work not being completed due to budget/procedures
INPROG | Duplicate service request where an existing service request has alread been progressed to a work order
NOPROBLEM | No Problem found
PENDING | Ready for Review
PRIVPROB | Private Problem; sent back to requestor
REFERRED | Referred to another jurisdiciton (does not belong to Pima County DOT)
RESOLVED | Work has been completed
TRANSFER | Maintenance sent to Community Relations to contact constituent
WOCREATED | Work Order Created (upcoming work planned)